## Sheet1
TEST # | TYPE OF TEST | TEST CATEGORY | TEST NAME | OWNER | PLANNED DATE | ACTUAL DATE | STATUS | ACTION ITEM | NOTES
1 | First Article | Test | Continuous Video | Ye | 2025-03-20 | 2025-02-14 | Passed |  |  | Color code
2 | First Article | Inspection | Image Resolution | Shahil | 2025-03-06 | 2025-03-06 | Passed | Function of the linear classifier, therefore postponed |  | Not Started
3 | First Article | Inspection | Inception Score | Shahil | 2025-03-06 |  | N/A | Inception score is only relevant when using a GAN, therefore no longer a relevant test |  | Passed
3.2 | First Article | Test | Signal throughput | Shahil | 2025-03-24 |  | Passed | Retrain model to be more consistent | Replacement for inception score test | In Progress
4 | First Article | Test | Total Protocol time | Jason | 2025-01-31 | 2025-02-06 | Passed |  | From the presentation starting to the end took 8 mins 56 secs | Postponed
5 | Acceptance Test | Test | Image Fidelity | Jason | 2025-03-06 |  | N/A | Image fidelity is only relevant when generating images with GAN
6 | Acceptance Test | Inspection | Video Coherence | Eason | 2025-03-20 |  | Passed |  |  | Failed
7 | First Article | Inspection | Open Source | Eason | 2025-04-08 | 2025-03-23 | Passed |  |  | N/A
8 | First Article | Demonstration | STL Fidelity (Optional) | Ye | 2025-04-08 | 2025-03-21 | Passed |  | Got some idea on that and it will working on it after other requirements are done
9 | First Article | Demonstration | Coding Process (Image) | Shahil | 2025-02-20 | 2025-03-06 | Passed | Switched to the linear classifier model and get the new program to run
10 | First Article | Demonstration | Coding Process (Video) | Ye | 2025-03-16 | 2025-02-13 | Passed |  | Took 5483.75 seconds to produce a 2 second long video from 2 images
11 | First Article | Demonstration | Coding Process (Stimulus) | Jason | 2025-01-31 | 2025-02-06 | Passed |  | Code runs with no issues and the interrupt works as intended
12 | First Article | Demonstration | Coding Process (Overall) | Eason | 2025-03-16 | 2025-03-16 | Passed